## Slide 1: Proposed GAC New gTLD Advice & Early Warning Processes 2012
  12th: Applications Open
Jan
  14th-19th: ICANN Toronto
  25th: Early Warning Period Ends
  30th: ACTUAL DATE TBD: Communication to GAC that Early Warning Portal is fully operational.
  13th: ICANN posts applications online
  17th: GAC Letter of Advice regarding timelines
  23-28: ICANN 44 – Prague
  11th-16th: ICANN San Jose
  TAS OFFLINE
  30th: Applications Close
Feb
  GAC new gTLD web portal is active, and GAC members request log-in details
Mar
Apr
May
  GAC Early Warning Web Portal Online and available for use
Jun
Jul
  GAC members use the wiki/discussion pages on EW Portal to coordinate and file Early Warnings
Aug
  GAC members use the wiki/discussion pages on EW Portal to coordinate and file Early Warnings
Sept
  14th-19th: GAC meets to discuss Early Warnings
  15th: High Level Meeting
  31st: Secretariat sends completed Early Warnings to ICANN for distribution to Applicants
Oct
  22nd : Reply period for Applicants to Early Warnings ends.
  GAC works intersessionally on Advice for contentious strings
  Oct 25th – Nov 14th: Secretariat fields new gTLD EW communications from applicants and posts on Portal
Nov
  GAC works intersessionally on Advice for contentious strings
Dec
ICANN New gTLD Milestones
GAC New gTLD Milestones

## Slide 2: Proposed GAC New gTLD Advice & Early Warning Processes 2013
  GAC works intersessionally on Advice for contentious strings
Jan
  14th-19th: ICANN 46: Africa
  7th-12th: ICANN 45: Beijing
  TBD: POSSIBLE INTER-SESSIONAL GAC MEETING
Feb
  GAC works intersessionally on Advice for contentious strings
Mar
  7th-12th: GAC meets to finalize GAC Advice
  30th: TBD: Final Date for GAC to provide Advice on new gTLDs
Apr
May
Jun
  14th-19th: GAC Meets – Taking stock of round 1
Jul
Aug
Sept
Oct
Nov
Dec
ICANN New gTLD Milestones
GAC New gTLD Milestones